## Gap Analysis
AI Maturity Gap Analysis — Meridian Healthcare
# | Recommendation | Timeline | Investment | Expected Impact | Owner
1 | Hire AI/ML Lead + 2 ML Engineers | Month 1-2 | $420K/yr | Unblock NLP pilot | CTO
2 | Deploy AI governance framework | Month 1-3 | $280K | HIPAA + EU AI Act readiness | CDO
3 | Implement MLflow for model management | Month 2-4 | $85K | NLP pilot to production in 6 weeks | AI/ML Lead
4 | Establish data quality program | Month 3-6 | $150K | Data quality 62% → 85% | Head of Gov
5 | Create dedicated AI budget line | Month 1 | $0 | Visibility and accountability | CFO
6 | Build use case pipeline process | Month 2-4 | $60K | Systematic AI opportunity capture | Use Case Lead